## Sheet1
Responsible | Task | Effort | Time
Vee | Replicate infastructure of tests Data Factory
Vee | Terraform Parameterization of Linked Service | 2
Vee | Terraform Parameterization of Datasets
Vee | Terraform Parameterization of Integration Runtime
Vee | Split the terraform files between DF Objects (factory, integration runtime, linked service, datasest)
Vee | Investigation KeyVault implementation of Linked Services
Vee | Implementation of Keyvault Linked Services
Vee | Obfuscation of Terraform secrets
Vee | Programatically export and import pipelines (ARM, Bicep, Terraform)
Vee | Include Pipeline export and import as part of wf
Vee | Create SQL Server through database | 1
Vee | Create SQL DB (Single Instance) through terraform
Vee | Deploy Master Data from ???
Vee | Drive terraform config file though database schema
Vee | Create Database Schemas
Vee | Deployment of Global Parameters
Vee | Specifying Global Parameters in the Terraform config file | 2
Vee | Bulk config of linked services
Vee | Config of Integration Runtime
Vee | Test case build of terraform template
Vee | Build pipeline for terraform
Vee | Update Resource ?
Vee | Logging?
Vee | Source Control TF
Front end for load config
versioning of tf templates
central db/way so we can know what version of template applied to which customers
deployment plan (do we keep all customers on latest version or is that customer dependent)
byok (bring your own crypto keys)
Logging of deployments centrally (azure monitor)
Automation of deployment (ie bulk deployments where templates updates)
deployments of Integration Runtimes
versioning and deployment of pipeline
versioning of metadata database and master data
database driven terraform configs
simple pbi of templates
change strategy when linked service params change
validation of deployments (can probably use az cli)
SQL DB --> SQL MASTER DATA POPULATION --> ADF --> IR --> LS --> DS --> PIPELINE DEPLOYMENTS
I am thinking now, can use az cli to do pipeline deployments and validations
we can build it into a workflow to have all in single process
* two more, document our wf in flow diagram
*build data transfer pipeline with databricks

## Sheet3
ID | Work Item Type | Title | Description | Priority | State | Effort | Completed Work | Tags | Assigned To
0 | Project | Metadata Driven Load Framework | Metadata Driven Load Framework | 2 | To Do
1000 | Epic | Terraform Resource Provisioning | Terraform Resource Provisioning | 2 | To Do
2000 | Epic | Metadata Database | Metadata Database | 2 | To Do
3000 | Epic | Azure Data Factory | Azure Data Factory | 2 | To Do
1100 | Feature | Terraform Investigation and Upskill | Terraform Investigation and Upskill | 2 | To Do | 40
1101 | Task | Create terraform template to deploy an Azure Resource Group | Create terraform template to deploy an Azure Resource Group | 2 | To Do | 2
1102 | Task | Create terraform template to deploy an Azure Data Factory into the Resource Group | Create terraform template to deploy an Azure Data Factory into the Resource Group | 2 | To Do | 4
1103 | Task | Create terraform template to deploy an Integration Runtime to the Azure Data Factory | Create terraform template to deploy an Integration Runtime to the Azure Data Factory | 2 | To Do | 4
1104 | Task | Create terraform template to deploy a static Database Linked Service to the Azure Data Factory | Create terraform template to deploy a static Database Linked Service to the Azure Data Factory | 2 | To Do | 2
1105 | Task | Create terraform template to deploy a static Azure Data Lake Storage (ADLS2) Linked Service to the Azure Data Factory | Create terraform template to deploy a static Azure Data Lake Storage (ADLS2) Linked Service to the Azure Data Factory | 2 | To Do | 2
1106 | Task | Create terraform template to deploy a static Dataset to the Azure Data Factory | Create terraform template to deploy a static Dataset to the Azure Data Factory | 2 | To Do | 2
1107 | Task | Create terraform template using Azure Keyvault secret | Create terraform template using Azure Keyvault secret | 3 | To Do | 4
1108 | Task | Determine how best to obfuscate template secrets | Determine how best to obfuscate template secrets | 3 | To Do | 4
1200 | Feature | Investigate whether Terraform is fit for purpose for the Metadata Driven Load Framework | Investigate whether Terraform is fit for purpose for the Metadata Driven Load Framework | 2 | To Do | 4
1201 | Task | Determine whether Terrarform should only be used for service deployment or artefact deployment as well | Determine whether Terrarform should only be used for service deployment or artefact deployment as well | 2 | To Do | 4
1202 | Task | Create ARM Template deployment provisioner for Linked Services | Create ARM Template deployment provisioner for Linked Services | 2 | To Do | 4
1203 | Task | Create ARM Template deployment provisioner for Datasets | Create ARM Template deployment provisioner for Datasets | 2 | To Do | 4
1204 | Task | Create ARM Template deployment provisioner for Pipelines | Create ARM Template deployment provisioner for Pipelines | 2 | To Do | 4
1205 | Task | Determine how Integration Runtimes will be deployed though terraform | Determine how Integration Runtimes will be deployed though terraform | 2 | To Do | 2
1300 | Feature | Azure Data Factory Build | Azure Data Factory Build | 2 | To Do
1301 | Task | Create a Development Data Factory | Create a Development Data Factory | 2 | To Do
1302 | Task | Create Parameterized Linked Service for AmazonMWSLinkedService | Create Parameterized Linked Service for AmazonMWSLinkedService | 2 | To Do | 1.5
1303 | Task | Create Parameterized Linked Service for AmazonRdsForOracleLinkedService | Create Parameterized Linked Service for AmazonRdsForOracleLinkedService | 2 | To Do | 1.5
1304 | Task | Create Parameterized Linked Service for AmazonRdsForSqlServerLinkedService | Create Parameterized Linked Service for AmazonRdsForSqlServerLinkedService | 2 | To Do | 1.5
1305 | Task | Create Parameterized Linked Service for AmazonRedshiftLinkedService | Create Parameterized Linked Service for AmazonRedshiftLinkedService | 2 | To Do | 1.5
1306 | Task | Create Parameterized Linked Service for AmazonS3CompatibleLinkedService | Create Parameterized Linked Service for AmazonS3CompatibleLinkedService | 2 | To Do | 1.5
1307 | Task | Create Parameterized Linked Service for AmazonS3LinkedService | Create Parameterized Linked Service for AmazonS3LinkedService | 2 | To Do | 1.5
1308 | Task | Create Parameterized Linked Service for AzureBatchLinkedService | Create Parameterized Linked Service for AzureBatchLinkedService | 2 | To Do | 1.5
1309 | Task | Create Parameterized Linked Service for AzureBlobFSLinkedService | Create Parameterized Linked Service for AzureBlobFSLinkedService | 2 | To Do | 1.5
1310 | Task | Create Parameterized Linked Service for AzureBlobStorageLinkedService | Create Parameterized Linked Service for AzureBlobStorageLinkedService | 2 | To Do | 1.5
1311 | Task | Create Parameterized Linked Service for AzureDatabricksDeltaLakeLinkedService | Create Parameterized Linked Service for AzureDatabricksDeltaLakeLinkedService | 2 | To Do | 1.5
1312 | Task | Create Parameterized Linked Service for AzureDatabricksLinkedService | Create Parameterized Linked Service for AzureDatabricksLinkedService | 2 | To Do | 1.5
1313 | Task | Create Parameterized Linked Service for AzureDataExplorerLinkedService | Create Parameterized Linked Service for AzureDataExplorerLinkedService | 2 | To Do | 1.5
1314 | Task | Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService | Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService | 2 | To Do | 1.5
1315 | Task | Create Parameterized Linked Service for AzureDataLakeStoreLinkedService | Create Parameterized Linked Service for AzureDataLakeStoreLinkedService | 2 | To Do | 1.5
1316 | Task | Create Parameterized Linked Service for AzureFileStorageLinkedService | Create Parameterized Linked Service for AzureFileStorageLinkedService | 2 | To Do | 1.5
1317 | Task | Create Parameterized Linked Service for AzureFunctionLinkedService | Create Parameterized Linked Service for AzureFunctionLinkedService | 2 | To Do | 1.5
1318 | Task | Create Parameterized Linked Service for AzureKeyVaultLinkedService | Create Parameterized Linked Service for AzureKeyVaultLinkedService | 2 | To Do | 1.5
1319 | Task | Create Parameterized Linked Service for AzureMariaDBLinkedService | Create Parameterized Linked Service for AzureMariaDBLinkedService | 2 | To Do | 1.5
1320 | Task | Create Parameterized Linked Service for AzureMLLinkedService | Create Parameterized Linked Service for AzureMLLinkedService | 2 | To Do | 1.5
1321 | Task | Create Parameterized Linked Service for AzureMLServiceLinkedService | Create Parameterized Linked Service for AzureMLServiceLinkedService | 2 | To Do | 1.5
1322 | Task | Create Parameterized Linked Service for AzureMySqlLinkedService | Create Parameterized Linked Service for AzureMySqlLinkedService | 2 | To Do | 1.5
1323 | Task | Create Parameterized Linked Service for AzurePostgreSqlLinkedService | Create Parameterized Linked Service for AzurePostgreSqlLinkedService | 2 | To Do | 1.5
1324 | Task | Create Parameterized Linked Service for AzureSearchLinkedService | Create Parameterized Linked Service for AzureSearchLinkedService | 2 | To Do | 1.5
1325 | Task | Create Parameterized Linked Service for AzureSqlDatabaseLinkedService | Create Parameterized Linked Service for AzureSqlDatabaseLinkedService | 2 | To Do | 1.5
1326 | Task | Create Parameterized Linked Service for AzureSqlDWLinkedService | Create Parameterized Linked Service for AzureSqlDWLinkedService | 2 | To Do | 1.5
1327 | Task | Create Parameterized Linked Service for AzureSqlMILinkedService | Create Parameterized Linked Service for AzureSqlMILinkedService | 2 | To Do | 1.5
1328 | Task | Create Parameterized Linked Service for AzureStorageLinkedService | Create Parameterized Linked Service for AzureStorageLinkedService | 2 | To Do | 1.5
1329 | Task | Create Parameterized Linked Service for AzureTableStorageLinkedService | Create Parameterized Linked Service for AzureTableStorageLinkedService | 2 | To Do | 1.5
1330 | Task | Create Parameterized Linked Service for CassandraLinkedService | Create Parameterized Linked Service for CassandraLinkedService | 2 | To Do | 1.5
1331 | Task | Create Parameterized Linked Service for CommonDataServiceForAppsLinkedService | Create Parameterized Linked Service for CommonDataServiceForAppsLinkedService | 2 | To Do | 1.5
1332 | Task | Create Parameterized Linked Service for ConcurLinkedService | Create Parameterized Linked Service for ConcurLinkedService | 2 | To Do | 1.5
1333 | Task | Create Parameterized Linked Service for CosmosDbLinkedService | Create Parameterized Linked Service for CosmosDbLinkedService | 2 | To Do | 1.5
1334 | Task | Create Parameterized Linked Service for CosmosDbMongoDbApiLinkedService | Create Parameterized Linked Service for CosmosDbMongoDbApiLinkedService | 2 | To Do | 1.5
1335 | Task | Create Parameterized Linked Service for CouchbaseLinkedService | Create Parameterized Linked Service for CouchbaseLinkedService | 2 | To Do | 1.5
1336 | Task | Create Parameterized Linked Service for CustomDataSourceLinkedService | Create Parameterized Linked Service for CustomDataSourceLinkedService | 2 | To Do | 1.5
1337 | Task | Create Parameterized Linked Service for Db2LinkedService | Create Parameterized Linked Service for Db2LinkedService | 2 | To Do | 1.5
1338 | Task | Create Parameterized Linked Service for DrillLinkedService | Create Parameterized Linked Service for DrillLinkedService | 2 | To Do | 1.5
1339 | Task | Create Parameterized Linked Service for DynamicsAXLinkedService | Create Parameterized Linked Service for DynamicsAXLinkedService | 2 | To Do | 1.5
1340 | Task | Create Parameterized Linked Service for DynamicsCrmLinkedService | Create Parameterized Linked Service for DynamicsCrmLinkedService | 2 | To Do | 1.5
1341 | Task | Create Parameterized Linked Service for DynamicsLinkedService | Create Parameterized Linked Service for DynamicsLinkedService | 2 | To Do | 1.5
1342 | Task | Create Parameterized Linked Service for EloquaLinkedService | Create Parameterized Linked Service for EloquaLinkedService | 2 | To Do | 1.5
1343 | Task | Create Parameterized Linked Service for FileServerLinkedService | Create Parameterized Linked Service for FileServerLinkedService | 2 | To Do | 1.5
1344 | Task | Create Parameterized Linked Service for FtpServerLinkedService | Create Parameterized Linked Service for FtpServerLinkedService | 2 | To Do | 1.5
1345 | Task | Create Parameterized Linked Service for GoogleAdWordsLinkedService | Create Parameterized Linked Service for GoogleAdWordsLinkedService | 2 | To Do | 1.5
1346 | Task | Create Parameterized Linked Service for GoogleBigQueryLinkedService | Create Parameterized Linked Service for GoogleBigQueryLinkedService | 2 | To Do | 1.5
1347 | Task | Create Parameterized Linked Service for GoogleCloudStorageLinkedService | Create Parameterized Linked Service for GoogleCloudStorageLinkedService | 2 | To Do | 1.5
1348 | Task | Create Parameterized Linked Service for GreenplumLinkedService | Create Parameterized Linked Service for GreenplumLinkedService | 2 | To Do | 1.5
1349 | Task | Create Parameterized Linked Service for HBaseLinkedService | Create Parameterized Linked Service for HBaseLinkedService | 2 | To Do | 1.5
1350 | Task | Create Parameterized Linked Service for HdfsLinkedService | Create Parameterized Linked Service for HdfsLinkedService | 2 | To Do | 1.5
1351 | Task | Create Parameterized Linked Service for HDInsightLinkedService | Create Parameterized Linked Service for HDInsightLinkedService | 2 | To Do | 1.5
1352 | Task | Create Parameterized Linked Service for HDInsightOnDemandLinkedService | Create Parameterized Linked Service for HDInsightOnDemandLinkedService | 2 | To Do | 1.5
1353 | Task | Create Parameterized Linked Service for HiveLinkedService | Create Parameterized Linked Service for HiveLinkedService | 2 | To Do | 1.5
1354 | Task | Create Parameterized Linked Service for HttpLinkedService | Create Parameterized Linked Service for HttpLinkedService | 2 | To Do | 1.5
1355 | Task | Create Parameterized Linked Service for HubspotLinkedService | Create Parameterized Linked Service for HubspotLinkedService | 2 | To Do | 1.5
1356 | Task | Create Parameterized Linked Service for ImpalaLinkedService | Create Parameterized Linked Service for ImpalaLinkedService | 2 | To Do | 1.5
1357 | Task | Create Parameterized Linked Service for InformixLinkedService | Create Parameterized Linked Service for InformixLinkedService | 2 | To Do | 1.5
1358 | Task | Create Parameterized Linked Service for JiraLinkedService | Create Parameterized Linked Service for JiraLinkedService | 2 | To Do | 1.5
1359 | Task | Create Parameterized Linked Service for MagentoLinkedService | Create Parameterized Linked Service for MagentoLinkedService | 2 | To Do | 1.5
1360 | Task | Create Parameterized Linked Service for MariaDBLinkedService | Create Parameterized Linked Service for MariaDBLinkedService | 2 | To Do | 1.5
1361 | Task | Create Parameterized Linked Service for MarketoLinkedService | Create Parameterized Linked Service for MarketoLinkedService | 2 | To Do | 1.5
1362 | Task | Create Parameterized Linked Service for MicrosoftAccessLinkedService | Create Parameterized Linked Service for MicrosoftAccessLinkedService | 2 | To Do | 1.5
1363 | Task | Create Parameterized Linked Service for MongoDbAtlasLinkedService | Create Parameterized Linked Service for MongoDbAtlasLinkedService | 2 | To Do | 1.5
1364 | Task | Create Parameterized Linked Service for MongoDbLinkedService | Create Parameterized Linked Service for MongoDbLinkedService | 2 | To Do | 1.5
1365 | Task | Create Parameterized Linked Service for MongoDbV2LinkedService | Create Parameterized Linked Service for MongoDbV2LinkedService | 2 | To Do | 1.5
1366 | Task | Create Parameterized Linked Service for MySqlLinkedService | Create Parameterized Linked Service for MySqlLinkedService | 2 | To Do | 1.5
1367 | Task | Create Parameterized Linked Service for NetezzaLinkedService | Create Parameterized Linked Service for NetezzaLinkedService | 2 | To Do | 1.5
1368 | Task | Create Parameterized Linked Service for ODataLinkedService | Create Parameterized Linked Service for ODataLinkedService | 2 | To Do | 1.5
1369 | Task | Create Parameterized Linked Service for OdbcLinkedService | Create Parameterized Linked Service for OdbcLinkedService | 2 | To Do | 1.5
1370 | Task | Create Parameterized Linked Service for Office365LinkedService | Create Parameterized Linked Service for Office365LinkedService | 2 | To Do | 1.5
1371 | Task | Create Parameterized Linked Service for OracleCloudStorageLinkedService | Create Parameterized Linked Service for OracleCloudStorageLinkedService | 2 | To Do | 1.5
1372 | Task | Create Parameterized Linked Service for OracleLinkedService | Create Parameterized Linked Service for OracleLinkedService | 2 | To Do | 1.5
1373 | Task | Create Parameterized Linked Service for OracleServiceCloudLinkedService | Create Parameterized Linked Service for OracleServiceCloudLinkedService | 2 | To Do | 1.5
1374 | Task | Create Parameterized Linked Service for PaypalLinkedService | Create Parameterized Linked Service for PaypalLinkedService | 2 | To Do | 1.5
1375 | Task | Create Parameterized Linked Service for PhoenixLinkedService | Create Parameterized Linked Service for PhoenixLinkedService | 2 | To Do | 1.5
1376 | Task | Create Parameterized Linked Service for PostgreSqlLinkedService | Create Parameterized Linked Service for PostgreSqlLinkedService | 2 | To Do | 1.5
1377 | Task | Create Parameterized Linked Service for PrestoLinkedService | Create Parameterized Linked Service for PrestoLinkedService | 2 | To Do | 1.5
1378 | Task | Create Parameterized Linked Service for QuickbaseLinkedService | Create Parameterized Linked Service for QuickbaseLinkedService | 2 | To Do | 1.5
1379 | Task | Create Parameterized Linked Service for QuickBooksLinkedService | Create Parameterized Linked Service for QuickBooksLinkedService | 2 | To Do | 1.5
1380 | Task | Create Parameterized Linked Service for ResponsysLinkedService | Create Parameterized Linked Service for ResponsysLinkedService | 2 | To Do | 1.5
1381 | Task | Create Parameterized Linked Service for RestServiceLinkedService | Create Parameterized Linked Service for RestServiceLinkedService | 2 | To Do | 1.5
1382 | Task | Create Parameterized Linked Service for SalesforceLinkedService | Create Parameterized Linked Service for SalesforceLinkedService | 2 | To Do | 1.5
1383 | Task | Create Parameterized Linked Service for SalesforceMarketingCloudLinkedService | Create Parameterized Linked Service for SalesforceMarketingCloudLinkedService | 2 | To Do | 1.5
1384 | Task | Create Parameterized Linked Service for SalesforceServiceCloudLinkedService | Create Parameterized Linked Service for SalesforceServiceCloudLinkedService | 2 | To Do | 1.5
1385 | Task | Create Parameterized Linked Service for SapBWLinkedService | Create Parameterized Linked Service for SapBWLinkedService | 2 | To Do | 1.5
1386 | Task | Create Parameterized Linked Service for SapCloudForCustomerLinkedService | Create Parameterized Linked Service for SapCloudForCustomerLinkedService | 2 | To Do | 1.5
1387 | Task | Create Parameterized Linked Service for SapEccLinkedService | Create Parameterized Linked Service for SapEccLinkedService | 2 | To Do | 1.5
1388 | Task | Create Parameterized Linked Service for SapHanaLinkedService | Create Parameterized Linked Service for SapHanaLinkedService | 2 | To Do | 1.5
1389 | Task | Create Parameterized Linked Service for SapOpenHubLinkedService | Create Parameterized Linked Service for SapOpenHubLinkedService | 2 | To Do | 1.5
1390 | Task | Create Parameterized Linked Service for SapTableLinkedService | Create Parameterized Linked Service for SapTableLinkedService | 2 | To Do | 1.5
1391 | Task | Create Parameterized Linked Service for ServiceNowLinkedService | Create Parameterized Linked Service for ServiceNowLinkedService | 2 | To Do | 1.5
1392 | Task | Create Parameterized Linked Service for SftpServerLinkedService | Create Parameterized Linked Service for SftpServerLinkedService | 2 | To Do | 1.5
1393 | Task | Create Parameterized Linked Service for SharePointOnlineListLinkedService | Create Parameterized Linked Service for SharePointOnlineListLinkedService | 2 | To Do | 1.5
1394 | Task | Create Parameterized Linked Service for ShopifyLinkedService | Create Parameterized Linked Service for ShopifyLinkedService | 2 | To Do | 1.5
1395 | Task | Create Parameterized Linked Service for SmartsheetLinkedService | Create Parameterized Linked Service for SmartsheetLinkedService | 2 | To Do | 1.5
1396 | Task | Create Parameterized Linked Service for SnowflakeLinkedService | Create Parameterized Linked Service for SnowflakeLinkedService | 2 | To Do | 1.5
1397 | Task | Create Parameterized Linked Service for SparkLinkedService | Create Parameterized Linked Service for SparkLinkedService | 2 | To Do | 1.5
1398 | Task | Create Parameterized Linked Service for SqlServerLinkedService | Create Parameterized Linked Service for SqlServerLinkedService | 2 | To Do | 1.5
1399 | Task | Create Parameterized Linked Service for SquareLinkedService | Create Parameterized Linked Service for SquareLinkedService | 2 | To Do | 1.5
1400 | Task | Create Parameterized Linked Service for SybaseLinkedService | Create Parameterized Linked Service for SybaseLinkedService | 2 | To Do | 1.5
1401 | Task | Create Parameterized Linked Service for TeamDeskLinkedService | Create Parameterized Linked Service for TeamDeskLinkedService | 2 | To Do | 1.5
1402 | Task | Create Parameterized Linked Service for TeradataLinkedService | Create Parameterized Linked Service for TeradataLinkedService | 2 | To Do | 1.5
1403 | Task | Create Parameterized Linked Service for VerticaLinkedService | Create Parameterized Linked Service for VerticaLinkedService | 2 | To Do | 1.5
1404 | Task | Create Parameterized Linked Service for WebLinkedService | Create Parameterized Linked Service for WebLinkedService | 2 | To Do | 1.5
1405 | Task | Create Parameterized Linked Service for XeroLinkedService | Create Parameterized Linked Service for XeroLinkedService | 2 | To Do | 1.5
1406 | Task | Create Parameterized Linked Service for ZendeskLinkedService | Create Parameterized Linked Service for ZendeskLinkedService | 2 | To Do | 1.5
1407 | Task | Create Parameterized Linked Service for ZohoLinkedService | Create Parameterized Linked Service for ZohoLinkedService | 2 | To Do | 1.5
1408 | Task | Create Parameterized Dataset for AmazonMWSLinkedService | Create Parameterized Dataset for AmazonMWSLinkedService | 2 | To Do | 1
1409 | Task | Create Parameterized Dataset for AmazonRdsForOracleLinkedService | Create Parameterized Dataset for AmazonRdsForOracleLinkedService | 2 | To Do | 1
1410 | Task | Create Parameterized Dataset for AmazonRdsForSqlServerLinkedService | Create Parameterized Dataset for AmazonRdsForSqlServerLinkedService | 2 | To Do | 1
1411 | Task | Create Parameterized Dataset for AmazonRedshiftLinkedService | Create Parameterized Dataset for AmazonRedshiftLinkedService | 2 | To Do | 1
1412 | Task | Create Parameterized Dataset for AmazonS3CompatibleLinkedService | Create Parameterized Dataset for AmazonS3CompatibleLinkedService | 2 | To Do | 1
1413 | Task | Create Parameterized Dataset for AmazonS3LinkedService | Create Parameterized Dataset for AmazonS3LinkedService | 2 | To Do | 1
1414 | Task | Create Parameterized Dataset for AzureBatchLinkedService | Create Parameterized Dataset for AzureBatchLinkedService | 2 | To Do | 1
1415 | Task | Create Parameterized Dataset for AzureBlobFSLinkedService | Create Parameterized Dataset for AzureBlobFSLinkedService | 2 | To Do | 1
1416 | Task | Create Parameterized Dataset for AzureBlobStorageLinkedService | Create Parameterized Dataset for AzureBlobStorageLinkedService | 2 | To Do | 1
1417 | Task | Create Parameterized Dataset for AzureDatabricksDeltaLakeLinkedService | Create Parameterized Dataset for AzureDatabricksDeltaLakeLinkedService | 2 | To Do | 1
1418 | Task | Create Parameterized Dataset for AzureDatabricksLinkedService | Create Parameterized Dataset for AzureDatabricksLinkedService | 2 | To Do | 1
1419 | Task | Create Parameterized Dataset for AzureDataExplorerLinkedService | Create Parameterized Dataset for AzureDataExplorerLinkedService | 2 | To Do | 1
1420 | Task | Create Parameterized Dataset for AzureDataLakeAnalyticsLinkedService | Create Parameterized Dataset for AzureDataLakeAnalyticsLinkedService | 8 | To Do | 1
1421 | Task | Create Parameterized Dataset for AzureDataLakeStoreLinkedService | Create Parameterized Dataset for AzureDataLakeStoreLinkedService | 8 | To Do | 1
1422 | Task | Create Parameterized Dataset for AzureFileStorageLinkedService | Create Parameterized Dataset for AzureFileStorageLinkedService | 2 | To Do | 1
1423 | Task | Create Parameterized Dataset for AzureFunctionLinkedService | Create Parameterized Dataset for AzureFunctionLinkedService | 2 | To Do | 1
1424 | Task | Create Parameterized Dataset for AzureKeyVaultLinkedService | Create Parameterized Dataset for AzureKeyVaultLinkedService | 2 | To Do | 1
1425 | Task | Create Parameterized Dataset for AzureMariaDBLinkedService | Create Parameterized Dataset for AzureMariaDBLinkedService | 2 | To Do | 1
1426 | Task | Create Parameterized Dataset for AzureMLLinkedService | Create Parameterized Dataset for AzureMLLinkedService | 2 | To Do | 1
1427 | Task | Create Parameterized Dataset for AzureMLServiceLinkedService | Create Parameterized Dataset for AzureMLServiceLinkedService | 2 | To Do | 1
1428 | Task | Create Parameterized Dataset for AzureMySqlLinkedService | Create Parameterized Dataset for AzureMySqlLinkedService | 2 | To Do | 1
1429 | Task | Create Parameterized Dataset for AzurePostgreSqlLinkedService | Create Parameterized Dataset for AzurePostgreSqlLinkedService | 2 | To Do | 1
1430 | Task | Create Parameterized Dataset for AzureSearchLinkedService | Create Parameterized Dataset for AzureSearchLinkedService | 2 | To Do | 1
1431 | Task | Create Parameterized Dataset for AzureSqlDatabaseLinkedService | Create Parameterized Dataset for AzureSqlDatabaseLinkedService | 2 | To Do | 1
1432 | Task | Create Parameterized Dataset for AzureSqlDWLinkedService | Create Parameterized Dataset for AzureSqlDWLinkedService | 2 | To Do | 1
1433 | Task | Create Parameterized Dataset for AzureSqlMILinkedService | Create Parameterized Dataset for AzureSqlMILinkedService | 2 | To Do | 1
1434 | Task | Create Parameterized Dataset for AzureStorageLinkedService | Create Parameterized Dataset for AzureStorageLinkedService | 2 | To Do | 1
1435 | Task | Create Parameterized Dataset for AzureTableStorageLinkedService | Create Parameterized Dataset for AzureTableStorageLinkedService | 2 | To Do | 1
1436 | Task | Create Parameterized Dataset for CassandraLinkedService | Create Parameterized Dataset for CassandraLinkedService | 2 | To Do | 1
1437 | Task | Create Parameterized Dataset for CommonDataServiceForAppsLinkedService | Create Parameterized Dataset for CommonDataServiceForAppsLinkedService | 2 | To Do | 1
1438 | Task | Create Parameterized Dataset for ConcurLinkedService | Create Parameterized Dataset for ConcurLinkedService | 2 | To Do | 1
1439 | Task | Create Parameterized Dataset for CosmosDbLinkedService | Create Parameterized Dataset for CosmosDbLinkedService | 2 | To Do | 1
1440 | Task | Create Parameterized Dataset for CosmosDbMongoDbApiLinkedService | Create Parameterized Dataset for CosmosDbMongoDbApiLinkedService | 2 | To Do | 1
1441 | Task | Create Parameterized Dataset for CouchbaseLinkedService | Create Parameterized Dataset for CouchbaseLinkedService | 2 | To Do | 1
1442 | Task | Create Parameterized Dataset for CustomDataSourceLinkedService | Create Parameterized Dataset for CustomDataSourceLinkedService | 2 | To Do | 1
1443 | Task | Create Parameterized Dataset for Db2LinkedService | Create Parameterized Dataset for Db2LinkedService | 2 | To Do | 1
1444 | Task | Create Parameterized Dataset for DrillLinkedService | Create Parameterized Dataset for DrillLinkedService | 2 | To Do | 1
1445 | Task | Create Parameterized Dataset for DynamicsAXLinkedService | Create Parameterized Dataset for DynamicsAXLinkedService | 2 | To Do | 1
1446 | Task | Create Parameterized Dataset for DynamicsCrmLinkedService | Create Parameterized Dataset for DynamicsCrmLinkedService | 2 | To Do | 1
1447 | Task | Create Parameterized Dataset for DynamicsLinkedService | Create Parameterized Dataset for DynamicsLinkedService | 2 | To Do | 1
1448 | Task | Create Parameterized Dataset for EloquaLinkedService | Create Parameterized Dataset for EloquaLinkedService | 2 | To Do | 1
1449 | Task | Create Parameterized Dataset for FileServerLinkedService | Create Parameterized Dataset for FileServerLinkedService | 2 | To Do | 1
1450 | Task | Create Parameterized Dataset for FtpServerLinkedService | Create Parameterized Dataset for FtpServerLinkedService | 2 | To Do | 1
1451 | Task | Create Parameterized Dataset for GoogleAdWordsLinkedService | Create Parameterized Dataset for GoogleAdWordsLinkedService | 2 | To Do | 1
1452 | Task | Create Parameterized Dataset for GoogleBigQueryLinkedService | Create Parameterized Dataset for GoogleBigQueryLinkedService | 2 | To Do | 1
1453 | Task | Create Parameterized Dataset for GoogleCloudStorageLinkedService | Create Parameterized Dataset for GoogleCloudStorageLinkedService | 2 | To Do | 1
1454 | Task | Create Parameterized Dataset for GreenplumLinkedService | Create Parameterized Dataset for GreenplumLinkedService | 2 | To Do | 1
1455 | Task | Create Parameterized Dataset for HBaseLinkedService | Create Parameterized Dataset for HBaseLinkedService | 2 | To Do | 1
1456 | Task | Create Parameterized Dataset for HdfsLinkedService | Create Parameterized Dataset for HdfsLinkedService | 2 | To Do | 1
1457 | Task | Create Parameterized Dataset for HDInsightLinkedService | Create Parameterized Dataset for HDInsightLinkedService | 2 | To Do | 1
1458 | Task | Create Parameterized Dataset for HDInsightOnDemandLinkedService | Create Parameterized Dataset for HDInsightOnDemandLinkedService | 2 | To Do | 1
1459 | Task | Create Parameterized Dataset for HiveLinkedService | Create Parameterized Dataset for HiveLinkedService | 2 | To Do | 1
1460 | Task | Create Parameterized Dataset for HttpLinkedService | Create Parameterized Dataset for HttpLinkedService | 2 | To Do | 1
1461 | Task | Create Parameterized Dataset for HubspotLinkedService | Create Parameterized Dataset for HubspotLinkedService | 2 | To Do | 1
1462 | Task | Create Parameterized Dataset for ImpalaLinkedService | Create Parameterized Dataset for ImpalaLinkedService | 2 | To Do | 1
1463 | Task | Create Parameterized Dataset for InformixLinkedService | Create Parameterized Dataset for InformixLinkedService | 2 | To Do | 1
1464 | Task | Create Parameterized Dataset for JiraLinkedService | Create Parameterized Dataset for JiraLinkedService | 2 | To Do | 1
1465 | Task | Create Parameterized Dataset for MagentoLinkedService | Create Parameterized Dataset for MagentoLinkedService | 2 | To Do | 1
1466 | Task | Create Parameterized Dataset for MariaDBLinkedService | Create Parameterized Dataset for MariaDBLinkedService | 2 | To Do | 1
1467 | Task | Create Parameterized Dataset for MarketoLinkedService | Create Parameterized Dataset for MarketoLinkedService | 2 | To Do | 1
1468 | Task | Create Parameterized Dataset for MicrosoftAccessLinkedService | Create Parameterized Dataset for MicrosoftAccessLinkedService | 2 | To Do | 1
1469 | Task | Create Parameterized Dataset for MongoDbAtlasLinkedService | Create Parameterized Dataset for MongoDbAtlasLinkedService | 2 | To Do | 1
1470 | Task | Create Parameterized Dataset for MongoDbLinkedService | Create Parameterized Dataset for MongoDbLinkedService | 2 | To Do | 1
1471 | Task | Create Parameterized Dataset for MongoDbV2LinkedService | Create Parameterized Dataset for MongoDbV2LinkedService | 2 | To Do | 1
1472 | Task | Create Parameterized Dataset for MySqlLinkedService | Create Parameterized Dataset for MySqlLinkedService | 2 | To Do | 1
1473 | Task | Create Parameterized Dataset for NetezzaLinkedService | Create Parameterized Dataset for NetezzaLinkedService | 2 | To Do | 1
1474 | Task | Create Parameterized Dataset for ODataLinkedService | Create Parameterized Dataset for ODataLinkedService | 2 | To Do | 1
1475 | Task | Create Parameterized Dataset for OdbcLinkedService | Create Parameterized Dataset for OdbcLinkedService | 2 | To Do | 1
1476 | Task | Create Parameterized Dataset for Office365LinkedService | Create Parameterized Dataset for Office365LinkedService | 2 | To Do | 1
1477 | Task | Create Parameterized Dataset for OracleCloudStorageLinkedService | Create Parameterized Dataset for OracleCloudStorageLinkedService | 2 | To Do | 1
1478 | Task | Create Parameterized Dataset for OracleLinkedService | Create Parameterized Dataset for OracleLinkedService | 2 | To Do | 1
1479 | Task | Create Parameterized Dataset for OracleServiceCloudLinkedService | Create Parameterized Dataset for OracleServiceCloudLinkedService | 2 | To Do | 1
1480 | Task | Create Parameterized Dataset for PaypalLinkedService | Create Parameterized Dataset for PaypalLinkedService | 2 | To Do | 1
1481 | Task | Create Parameterized Dataset for PhoenixLinkedService | Create Parameterized Dataset for PhoenixLinkedService | 2 | To Do | 1
1482 | Task | Create Parameterized Dataset for PostgreSqlLinkedService | Create Parameterized Dataset for PostgreSqlLinkedService | 2 | To Do | 1
1483 | Task | Create Parameterized Dataset for PrestoLinkedService | Create Parameterized Dataset for PrestoLinkedService | 2 | To Do | 1
1484 | Task | Create Parameterized Dataset for QuickbaseLinkedService | Create Parameterized Dataset for QuickbaseLinkedService | 2 | To Do | 1
1485 | Task | Create Parameterized Dataset for QuickBooksLinkedService | Create Parameterized Dataset for QuickBooksLinkedService | 2 | To Do | 1
1486 | Task | Create Parameterized Dataset for ResponsysLinkedService | Create Parameterized Dataset for ResponsysLinkedService | 2 | To Do | 1
1487 | Task | Create Parameterized Dataset for RestServiceLinkedService | Create Parameterized Dataset for RestServiceLinkedService | 2 | To Do | 1
1488 | Task | Create Parameterized Dataset for SalesforceLinkedService | Create Parameterized Dataset for SalesforceLinkedService | 2 | To Do | 1
1489 | Task | Create Parameterized Dataset for SalesforceMarketingCloudLinkedService | Create Parameterized Dataset for SalesforceMarketingCloudLinkedService | 2 | To Do | 1
1490 | Task | Create Parameterized Dataset for SalesforceServiceCloudLinkedService | Create Parameterized Dataset for SalesforceServiceCloudLinkedService | 2 | To Do | 1
1491 | Task | Create Parameterized Dataset for SapBWLinkedService | Create Parameterized Dataset for SapBWLinkedService | 2 | To Do | 1
1492 | Task | Create Parameterized Dataset for SapCloudForCustomerLinkedService | Create Parameterized Dataset for SapCloudForCustomerLinkedService | 2 | To Do | 1
1493 | Task | Create Parameterized Dataset for SapEccLinkedService | Create Parameterized Dataset for SapEccLinkedService | 2 | To Do | 1
1494 | Task | Create Parameterized Dataset for SapHanaLinkedService | Create Parameterized Dataset for SapHanaLinkedService | 2 | To Do | 1
1495 | Task | Create Parameterized Dataset for SapOpenHubLinkedService | Create Parameterized Dataset for SapOpenHubLinkedService | 2 | To Do | 1
1496 | Task | Create Parameterized Dataset for SapTableLinkedService | Create Parameterized Dataset for SapTableLinkedService | 2 | To Do | 1
1497 | Task | Create Parameterized Dataset for ServiceNowLinkedService | Create Parameterized Dataset for ServiceNowLinkedService | 2 | To Do | 1
1498 | Task | Create Parameterized Dataset for SftpServerLinkedService | Create Parameterized Dataset for SftpServerLinkedService | 2 | To Do | 1
1499 | Task | Create Parameterized Dataset for SharePointOnlineListLinkedService | Create Parameterized Dataset for SharePointOnlineListLinkedService | 2 | To Do | 1
1500 | Task | Create Parameterized Dataset for ShopifyLinkedService | Create Parameterized Dataset for ShopifyLinkedService | 2 | To Do | 1
1501 | Task | Create Parameterized Dataset for SmartsheetLinkedService | Create Parameterized Dataset for SmartsheetLinkedService | 2 | To Do | 1
1502 | Task | Create Parameterized Dataset for SnowflakeLinkedService | Create Parameterized Dataset for SnowflakeLinkedService | 2 | To Do | 1
1503 | Task | Create Parameterized Dataset for SparkLinkedService | Create Parameterized Dataset for SparkLinkedService | 2 | To Do | 1
1504 | Task | Create Parameterized Dataset for SqlServerLinkedService | Create Parameterized Dataset for SqlServerLinkedService | 2 | To Do | 1
1505 | Task | Create Parameterized Dataset for SquareLinkedService | Create Parameterized Dataset for SquareLinkedService | 2 | To Do | 1
1506 | Task | Create Parameterized Dataset for SybaseLinkedService | Create Parameterized Dataset for SybaseLinkedService | 2 | To Do | 1
1507 | Task | Create Parameterized Dataset for TeamDeskLinkedService | Create Parameterized Dataset for TeamDeskLinkedService | 2 | To Do | 1
1508 | Task | Create Parameterized Dataset for TeradataLinkedService | Create Parameterized Dataset for TeradataLinkedService | 2 | To Do | 1
1509 | Task | Create Parameterized Dataset for VerticaLinkedService | Create Parameterized Dataset for VerticaLinkedService | 2 | To Do | 1
1510 | Task | Create Parameterized Dataset for WebLinkedService | Create Parameterized Dataset for WebLinkedService | 2 | To Do | 1
1511 | Task | Create Parameterized Dataset for XeroLinkedService | Create Parameterized Dataset for XeroLinkedService | 2 | To Do | 1
1512 | Task | Create Parameterized Dataset for ZendeskLinkedService | Create Parameterized Dataset for ZendeskLinkedService | 2 | To Do | 1
1513 | Task | Create Parameterized Dataset for ZohoLinkedService | Create Parameterized Dataset for ZohoLinkedService | 2 | To Do | 1
1514 | Task | Create Source target Pipeline for combinations of Linked Serivces | Create Source target Pipeline for combinations of Linked Serivces | 2 | To Do | 150
1515 | Task | Create Full Load Batch Type Pipeline | Create Full Load Batch Type Pipeline | 1 | To Do | 4
1516 | Task | Create Delta Batch Load type Pipeline | Create Delta Batch Load type Pipeline | 1 | To Do | 8
1517 | Task | Create Stream Load Pipeline | Create Stream Load Pipeline | 2 | To Do | 40
1518 | Task | Create Resource Scaling Pipeline | Create Resource Scaling Pipeline | 3 | To Do | 16
1519 | Task | Create Execution Activation Pipeline | Create Execution Activation Pipeline | 1 | To Do | 1
1520 | Task | Create Scheduled Runs Pipeine | Create Scheduled Runs Pipeine | 1 | To Do | 4
1521 | Task | Create Global Datafactory Parameters | Create Global Datafactory Parameters | 1 | To Do
1522 | Task | Configure Data Factory to git | Configure Data Factory to git | 1 | To Do
1600 | Feature | Terraform Build | Terraform Build | 2 | To Do
1601 | Task | Create Service Pincipal terraform module | Create Service Pincipal terraform module | 2 | To Do | 2
1602 | Task | Create Resource Group terraform module | Create Resource Group terraform module | 1 | To Do
1603 | Task | Create Azure Data Factory terraform module | Create Azure Data Factory terraform module | 2 | To Do | 2
1604 | Task | Create Integration Runtime terraform module | Create Integration Runtime terraform module | 2 | To Do | 2
1605 | Task | Create KeyVault terraform module | Create KeyVault terraform module | 2 | To Do | 2
1606 | Task | Create SQL Database terraform module | Create SQL Database terraform module | 2 | To Do | 2
1607 | Task | Create Synapse Serverless terraform module | Create Synapse Serverless terraform module | 2 | To Do | 2
1608 | Task | Create Synapse Provisioned terraform module | Create Synapse Provisioned terraform module | 2 | To Do | 4
1609 | Task | Create Databricks terraform module | Create Databricks terraform module | 2 | To Do | 4
1610 | Task | Create Log Analytics terraform module | Create Log Analytics terraform module | 2 | To Do | 4
1611 | Task | Create Event Hub terraform module | Create Event Hub terraform module | 2 | To Do | 4
1612 | Task | Create Streaming Analytics terraform module | Create Streaming Analytics terraform module | 2 | To Do | 4
1613 | Task | Create notification hub terraform module | Create notification hub terraform module | 3 | To Do | 2
1614 | Task | Creat storage account terraform module | Creat storage account terraform module | 2 | To Do
1615 | Task | Create Data Lake storage account terraform Module | Create Data Lake storage account terraform Module | 2 | To Do
1700 | Feature | Terraform Documentation | Terraform Documentation
1701 | Task | Create Terraform Quickstart guide | Create Terraform Quickstart guide | 2 | To Do | 3
1702 | Task | Document Main.tf | Document Main.tf | 2 | To Do | 1
1703 | Task | Document ADF terraform module | Document ADF terraform module | 2 | To Do | 1
1704 | Task | Document Integration Runtime terraform module | Document Integration Runtime terraform module | 2 | To Do | 1
1705 | Task | Document KeyVault terraform module | Document KeyVault terraform module | 2 | To Do | 1
1706 | Task | Document SQL Database terraform module | Document SQL Database terraform module | 2 | To Do | 1
1707 | Task | Document Synapse Serverless terraform module | Document Synapse Serverless terraform module | 2 | To Do | 1
1708 | Task | Document Synapse Provisioned terraform module | Document Synapse Provisioned terraform module | 2 | To Do | 1
1709 | Task | Document Databricks terraform module | Document Databricks terraform module | 2 | To Do | 1
1710 | Task | Document Log Analytics terraform module | Document Log Analytics terraform module | 2 | To Do | 1
1711 | Task | Document Event Hub terraform module | Document Event Hub terraform module | 2 | To Do | 1
1712 | Task | Document Streaming Analytics terraform module | Document Streaming Analytics terraform module | 2 | To Do | 1
1713 | Task | Document notification hub terraform module | Document notification hub terraform module | 2 | To Do | 1
1715 | Task | Document providers.tf | Document providers.tf | 2 | To Do | 1
1716 | Task | Document variables.tf | Document variables.tf | 2 | To Do | 1
1717 | Task | Document output.tf | Document output.tf | 2 | To Do | 1
1718 | Task | Create visual representation of terraform workflow | Create visual representation of terraform workflow | 3 | To Do | 4
1800 | Feature | Metadata Database | Metadata Database
1801 | Task | Metadata Database Shema Design (ERD) | Metadata Database Shema Design (ERD) | 1 | To Do | 32
1802 | Task | Creation of Master Data for framework | Creation of Master Data for framework | 1 | To Do | 16
1803 | Task | Creation of Test Cases for every load type | Creation of Test Cases for every load type | 2 | To Do | 40
1804 | Task | Creation of Scheduling Views | Creation of Scheduling Views | 1 | To Do | 24
1805 | Task | Creation of Load Config Views | Creation of Load Config Views | 1 | To Do | 16
1806 | Task | Creation fo Watermark Views | Creation fo Watermark Views | 1 | To Do | 16
1807 | Task | Creation of Config mappings | Creation of Config mappings | 1 | To Do | 40
1900 | Feature | Build Pipeline | Build Pipeline
1901 |  | Creation of Parameterized DevOps Build pipeline for terraform | Creation of Parameterized DevOps Build pipeline for terraform | 3 | To Do | 16
1902 |  | Creation of parameterized DevOps Build pipeline for master data | Creation of parameterized DevOps Build pipeline for master data | 3 | To Do | 16
2000 | Feature | Release Pipeline | Release Pipeline
2001 | Task | Creation of Parameterized DevOps Release pipeline for terraform | Creation of Parameterized DevOps Release pipeline for terraform | 3 | To Do | 16
2002 | Task | Creation of parameterized DevOps Release pipeline for master data | Creation of parameterized DevOps Release pipeline for master data | 3 | To Do | 16
|  | Replicate infastructure of tests Data Factory | Create Parameterized Linked Service for AzureSqlDatabaseLinkedService
|  | Terraform Parameterization of Linked Service | Create Parameterized Linked Service for AzureSqlDWLinkedService
|  | Terraform Parameterization of Datasets | Create Parameterized Linked Service for AzureSqlMILinkedService
|  | Terraform Parameterization of Integration Runtime | Create Parameterized Linked Service for AzureStorageLinkedService
|  | Split the terraform files between DF Objects (factory, integration runtime, linked service, datasest) | Create Parameterized Linked Service for AzureTableStorageLinkedService
|  | Investigation KeyVault implementation of Linked Services | Create Parameterized Linked Service for CassandraLinkedService
|  | Implementation of Keyvault Linked Services | Create Parameterized Linked Service for CommonDataServiceForAppsLinkedService
|  | Obfuscation of Terraform secrets | Create Parameterized Linked Service for ConcurLinkedService
|  | Programatically export and import pipelines (ARM, Bicep, Terraform) | Create Parameterized Linked Service for CosmosDbLinkedService
|  | Include Pipeline export and import as part of wf | Create Parameterized Linked Service for CosmosDbMongoDbApiLinkedService
|  | Create SQL Server through database | Create Parameterized Linked Service for CouchbaseLinkedService
|  | Create SQL DB (Single Instance) through terraform | Create Parameterized Linked Service for CustomDataSourceLinkedService
|  | Deploy Master Data from ??? | Create Parameterized Linked Service for Db2LinkedService
|  | Drive terraform config file though database schema | Create Parameterized Linked Service for DrillLinkedService
|  | Create Database Schemas | Create Parameterized Linked Service for DynamicsAXLinkedService
|  | Deployment of Global Parameters | Create Parameterized Linked Service for DynamicsCrmLinkedService
|  | Specifying Global Parameters in the Terraform config file | Create Parameterized Linked Service for DynamicsLinkedService
|  | Bulk config of linked services | Create Parameterized Linked Service for EloquaLinkedService
|  | Config of Integration Runtime | Create Parameterized Linked Service for FileServerLinkedService
|  | Test case build of terraform template | Create Parameterized Linked Service for FtpServerLinkedService
|  | Build pipeline for terraform | Create Parameterized Linked Service for GoogleAdWordsLinkedService
|  | Update Resource ? | Create Parameterized Linked Service for GoogleBigQueryLinkedService
|  | Logging? | Create Parameterized Linked Service for GoogleCloudStorageLinkedService
|  | Source Control TF | Create Parameterized Linked Service for GreenplumLinkedService
|  | Front end for load config | Create Parameterized Linked Service for HBaseLinkedService
|  | versioning of tf templates | Create Parameterized Linked Service for HdfsLinkedService
|  | central db/way so we can know what version of template applied to which customers | Create Parameterized Linked Service for HDInsightLinkedService
|  | deployment plan (do we keep all customers on latest version or is that customer dependent) | Create Parameterized Linked Service for HDInsightOnDemandLinkedService
|  | byok (bring your own crypto keys) | Create Parameterized Linked Service for HiveLinkedService
|  | Logging of deployments centrally (azure monitor) | Create Parameterized Linked Service for HttpLinkedService
|  | Automation of deployment (ie bulk deployments where templates updates) | Create Parameterized Linked Service for HubspotLinkedService
|  | deployments of Integration Runtimes | Create Parameterized Linked Service for ImpalaLinkedService
|  | versioning and deployment of pipeline | Create Parameterized Linked Service for InformixLinkedService
|  | versioning of metadata database and master data | Create Parameterized Linked Service for JiraLinkedService
|  | database driven terraform configs | Create Parameterized Linked Service for MagentoLinkedService
|  | simple pbi of templates | Create Parameterized Linked Service for MariaDBLinkedService
|  | change strategy when linked service params change | Create Parameterized Linked Service for MarketoLinkedService
|  | validation of deployments (can probably use az cli) | Create Parameterized Linked Service for MicrosoftAccessLinkedService
|  | SQL DB --> SQL MASTER DATA POPULATION --> ADF --> IR --> LS --> DS --> PIPELINE DEPLOYMENTS | Create Parameterized Linked Service for MongoDbAtlasLinkedService
|  | I am thinking now, can use az cli to do pipeline deployments and validations | Create Parameterized Linked Service for MongoDbLinkedService
|  | we can build it into a workflow to have all in single process | Create Parameterized Linked Service for MongoDbV2LinkedService
|  | * two more, document our wf in flow diagram | Create Parameterized Linked Service for MySqlLinkedService
|  | *build data transfer pipeline with databricks | Create Parameterized Linked Service for NetezzaLinkedService
Create Parameterized Linked Service for ODataLinkedService
Create Parameterized Linked Service for OdbcLinkedService
Create Parameterized Linked Service for Office365LinkedService
Create Parameterized Linked Service for OracleCloudStorageLinkedService
Create Parameterized Linked Service for OracleLinkedService
Create Parameterized Linked Service for OracleServiceCloudLinkedService
| 1400 | Feature | Build Pipeline | #VALUE!
| 1500 | Feature | Release Pipeline | #VALUE!
Create Parameterized Linked Service for PostgreSqlLinkedService
Create Parameterized Linked Service for PrestoLinkedService
Create Parameterized Linked Service for QuickbaseLinkedService
Create Parameterized Linked Service for QuickBooksLinkedService
Create Parameterized Linked Service for ResponsysLinkedService
Create Parameterized Linked Service for RestServiceLinkedService
Create Parameterized Linked Service for SalesforceLinkedService
Create Parameterized Linked Service for SalesforceMarketingCloudLinkedService
Create Parameterized Linked Service for SalesforceServiceCloudLinkedService
Create Parameterized Linked Service for SapBWLinkedService
Create Parameterized Linked Service for SapCloudForCustomerLinkedService
Create Parameterized Linked Service for SapEccLinkedService
Create Parameterized Linked Service for SapHanaLinkedService
Create Parameterized Linked Service for SapOpenHubLinkedService
Create Parameterized Linked Service for SapTableLinkedService
Create Parameterized Linked Service for ServiceNowLinkedService
Create Parameterized Linked Service for SftpServerLinkedService
Create Parameterized Linked Service for SharePointOnlineListLinkedService
Create Parameterized Linked Service for ShopifyLinkedService
Create Parameterized Linked Service for SmartsheetLinkedService
Create Parameterized Linked Service for SnowflakeLinkedService
Create Parameterized Linked Service for SparkLinkedService
Create Parameterized Linked Service for SqlServerLinkedService
Create Parameterized Linked Service for SquareLinkedService
Create Parameterized Linked Service for SybaseLinkedService
Create Parameterized Linked Service for TeamDeskLinkedService
Create Parameterized Linked Service for TeradataLinkedService
Create Parameterized Linked Service for VerticaLinkedService
Create Parameterized Linked Service for WebLinkedService
Create Parameterized Linked Service for XeroLinkedService
Create Parameterized Linked Service for ZendeskLinkedService
Create Parameterized Linked Service for ZohoLinkedService

## Sheet9
Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService | Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService
Create Parameterized Linked Service for AzureKeyVaultLinkedService | Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService
Create Parameterized Linked Service for AzureMySqlLinkedService | Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService
Create Parameterized Linked Service for AzurePostgreSqlLinkedService | Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService
Create Parameterized Linked Service for AzureSqlDatabaseLinkedService | Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService
Create Parameterized Linked Service for HttpLinkedService | Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService
Create Parameterized Linked Service for SqlServerLinkedService | Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService
switch statement
Create Parameterized Linked Service for AzureMySqlLinkedService | Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService | Create Parameterized Linked Service for AzureSqlDatabaseLinkedService

## Sheet10
LoadConfig
LINKED SERVICE (PARAM) |  | ESTATE CUSTOMER
SERVERNAME @SERVERNAME_GENERIC |  | SERVERNAME franssql.datasbase.windows.net

## Sheet6
Question
Various ways to create linked service
Dfferent Filetypes will split the pipelines even futher

## Sheet2
DATA FACTORY (PARAMETERIZED HILL) | META DATA DATABASE (LOAD CONFIGS)
GLOBAL
|  | LINKED SERVICE |  | LINKED SERVICE
DATA FACTORY (PARAMETERIZED HILL) | META DATA DATABASE (LOAD CONFIGS) | DATASET | DATASET | DATASET | DATASET
|  | PIPELINES | PIPELINES | PIPELINES | PIPELINES
|  | PIPELINES | PIPELINES | PIPELINES | PIPELINES
|  | PIPELINES | PIPELINES | PIPELINES | PIPELINES

## Sheet4
Project
Epic
Feature
Requirement
Task

## Linked Service
LinkedService: | Pr
AmazonMWSLinkedService |  | Create Parameterized Linked Service for AmazonMWSLinkedService | Create Parameterized Dataset for AmazonMWSLinkedService
AmazonRdsForOracleLinkedService |  | Create Parameterized Linked Service for AmazonRdsForOracleLinkedService | Create Parameterized Dataset for AmazonRdsForOracleLinkedService
AmazonRdsForSqlServerLinkedService |  | Create Parameterized Linked Service for AmazonRdsForSqlServerLinkedService | Create Parameterized Dataset for AmazonRdsForSqlServerLinkedService
AmazonRedshiftLinkedService |  | Create Parameterized Linked Service for AmazonRedshiftLinkedService | Create Parameterized Dataset for AmazonRedshiftLinkedService
AmazonS3CompatibleLinkedService |  | Create Parameterized Linked Service for AmazonS3CompatibleLinkedService | Create Parameterized Dataset for AmazonS3CompatibleLinkedService
AmazonS3LinkedService |  | Create Parameterized Linked Service for AmazonS3LinkedService | Create Parameterized Dataset for AmazonS3LinkedService
AzureBatchLinkedService |  | Create Parameterized Linked Service for AzureBatchLinkedService | Create Parameterized Dataset for AzureBatchLinkedService
AzureBlobFSLinkedService |  | Create Parameterized Linked Service for AzureBlobFSLinkedService | Create Parameterized Dataset for AzureBlobFSLinkedService
AzureBlobStorageLinkedService |  | Create Parameterized Linked Service for AzureBlobStorageLinkedService | Create Parameterized Dataset for AzureBlobStorageLinkedService
AzureDatabricksDeltaLakeLinkedService |  | Create Parameterized Linked Service for AzureDatabricksDeltaLakeLinkedService | Create Parameterized Dataset for AzureDatabricksDeltaLakeLinkedService
AzureDatabricksLinkedService |  | Create Parameterized Linked Service for AzureDatabricksLinkedService | Create Parameterized Dataset for AzureDatabricksLinkedService
AzureDataExplorerLinkedService |  | Create Parameterized Linked Service for AzureDataExplorerLinkedService | Create Parameterized Dataset for AzureDataExplorerLinkedService
AzureDataLakeAnalyticsLinkedService |  | Create Parameterized Linked Service for AzureDataLakeAnalyticsLinkedService | Create Parameterized Dataset for AzureDataLakeAnalyticsLinkedService
AzureDataLakeStoreLinkedService |  | Create Parameterized Linked Service for AzureDataLakeStoreLinkedService | Create Parameterized Dataset for AzureDataLakeStoreLinkedService
AzureFileStorageLinkedService |  | Create Parameterized Linked Service for AzureFileStorageLinkedService | Create Parameterized Dataset for AzureFileStorageLinkedService
AzureFunctionLinkedService |  | Create Parameterized Linked Service for AzureFunctionLinkedService | Create Parameterized Dataset for AzureFunctionLinkedService
AzureKeyVaultLinkedService |  | Create Parameterized Linked Service for AzureKeyVaultLinkedService | Create Parameterized Dataset for AzureKeyVaultLinkedService
AzureMariaDBLinkedService |  | Create Parameterized Linked Service for AzureMariaDBLinkedService | Create Parameterized Dataset for AzureMariaDBLinkedService
AzureMLLinkedService |  | Create Parameterized Linked Service for AzureMLLinkedService | Create Parameterized Dataset for AzureMLLinkedService
AzureMLServiceLinkedService |  | Create Parameterized Linked Service for AzureMLServiceLinkedService | Create Parameterized Dataset for AzureMLServiceLinkedService
AzureMySqlLinkedService |  | Create Parameterized Linked Service for AzureMySqlLinkedService | Create Parameterized Dataset for AzureMySqlLinkedService
AzurePostgreSqlLinkedService |  | Create Parameterized Linked Service for AzurePostgreSqlLinkedService | Create Parameterized Dataset for AzurePostgreSqlLinkedService
AzureSearchLinkedService |  | Create Parameterized Linked Service for AzureSearchLinkedService | Create Parameterized Dataset for AzureSearchLinkedService
AzureSqlDatabaseLinkedService |  | Create Parameterized Linked Service for AzureSqlDatabaseLinkedService | Create Parameterized Dataset for AzureSqlDatabaseLinkedService
AzureSqlDWLinkedService |  | Create Parameterized Linked Service for AzureSqlDWLinkedService | Create Parameterized Dataset for AzureSqlDWLinkedService
AzureSqlMILinkedService |  | Create Parameterized Linked Service for AzureSqlMILinkedService | Create Parameterized Dataset for AzureSqlMILinkedService
AzureStorageLinkedService |  | Create Parameterized Linked Service for AzureStorageLinkedService | Create Parameterized Dataset for AzureStorageLinkedService
AzureTableStorageLinkedService |  | Create Parameterized Linked Service for AzureTableStorageLinkedService | Create Parameterized Dataset for AzureTableStorageLinkedService
CassandraLinkedService |  | Create Parameterized Linked Service for CassandraLinkedService | Create Parameterized Dataset for CassandraLinkedService
CommonDataServiceForAppsLinkedService |  | Create Parameterized Linked Service for CommonDataServiceForAppsLinkedService | Create Parameterized Dataset for CommonDataServiceForAppsLinkedService
ConcurLinkedService |  | Create Parameterized Linked Service for ConcurLinkedService | Create Parameterized Dataset for ConcurLinkedService
CosmosDbLinkedService |  | Create Parameterized Linked Service for CosmosDbLinkedService | Create Parameterized Dataset for CosmosDbLinkedService
CosmosDbMongoDbApiLinkedService |  | Create Parameterized Linked Service for CosmosDbMongoDbApiLinkedService | Create Parameterized Dataset for CosmosDbMongoDbApiLinkedService
CouchbaseLinkedService |  | Create Parameterized Linked Service for CouchbaseLinkedService | Create Parameterized Dataset for CouchbaseLinkedService
CustomDataSourceLinkedService |  | Create Parameterized Linked Service for CustomDataSourceLinkedService | Create Parameterized Dataset for CustomDataSourceLinkedService
Db2LinkedService |  | Create Parameterized Linked Service for Db2LinkedService | Create Parameterized Dataset for Db2LinkedService
DrillLinkedService |  | Create Parameterized Linked Service for DrillLinkedService | Create Parameterized Dataset for DrillLinkedService
DynamicsAXLinkedService |  | Create Parameterized Linked Service for DynamicsAXLinkedService | Create Parameterized Dataset for DynamicsAXLinkedService
DynamicsCrmLinkedService |  | Create Parameterized Linked Service for DynamicsCrmLinkedService | Create Parameterized Dataset for DynamicsCrmLinkedService
DynamicsLinkedService |  | Create Parameterized Linked Service for DynamicsLinkedService | Create Parameterized Dataset for DynamicsLinkedService
EloquaLinkedService |  | Create Parameterized Linked Service for EloquaLinkedService | Create Parameterized Dataset for EloquaLinkedService
FileServerLinkedService |  | Create Parameterized Linked Service for FileServerLinkedService | Create Parameterized Dataset for FileServerLinkedService
FtpServerLinkedService |  | Create Parameterized Linked Service for FtpServerLinkedService | Create Parameterized Dataset for FtpServerLinkedService
GoogleAdWordsLinkedService |  | Create Parameterized Linked Service for GoogleAdWordsLinkedService | Create Parameterized Dataset for GoogleAdWordsLinkedService
GoogleBigQueryLinkedService |  | Create Parameterized Linked Service for GoogleBigQueryLinkedService | Create Parameterized Dataset for GoogleBigQueryLinkedService
GoogleCloudStorageLinkedService |  | Create Parameterized Linked Service for GoogleCloudStorageLinkedService | Create Parameterized Dataset for GoogleCloudStorageLinkedService
GreenplumLinkedService |  | Create Parameterized Linked Service for GreenplumLinkedService | Create Parameterized Dataset for GreenplumLinkedService
HBaseLinkedService |  | Create Parameterized Linked Service for HBaseLinkedService | Create Parameterized Dataset for HBaseLinkedService
HdfsLinkedService |  | Create Parameterized Linked Service for HdfsLinkedService | Create Parameterized Dataset for HdfsLinkedService
HDInsightLinkedService |  | Create Parameterized Linked Service for HDInsightLinkedService | Create Parameterized Dataset for HDInsightLinkedService
HDInsightOnDemandLinkedService |  | Create Parameterized Linked Service for HDInsightOnDemandLinkedService | Create Parameterized Dataset for HDInsightOnDemandLinkedService
HiveLinkedService |  | Create Parameterized Linked Service for HiveLinkedService | Create Parameterized Dataset for HiveLinkedService
HttpLinkedService |  | Create Parameterized Linked Service for HttpLinkedService | Create Parameterized Dataset for HttpLinkedService
HubspotLinkedService |  | Create Parameterized Linked Service for HubspotLinkedService | Create Parameterized Dataset for HubspotLinkedService
ImpalaLinkedService |  | Create Parameterized Linked Service for ImpalaLinkedService | Create Parameterized Dataset for ImpalaLinkedService
InformixLinkedService |  | Create Parameterized Linked Service for InformixLinkedService | Create Parameterized Dataset for InformixLinkedService
JiraLinkedService |  | Create Parameterized Linked Service for JiraLinkedService | Create Parameterized Dataset for JiraLinkedService
MagentoLinkedService |  | Create Parameterized Linked Service for MagentoLinkedService | Create Parameterized Dataset for MagentoLinkedService
MariaDBLinkedService |  | Create Parameterized Linked Service for MariaDBLinkedService | Create Parameterized Dataset for MariaDBLinkedService
MarketoLinkedService |  | Create Parameterized Linked Service for MarketoLinkedService | Create Parameterized Dataset for MarketoLinkedService
MicrosoftAccessLinkedService |  | Create Parameterized Linked Service for MicrosoftAccessLinkedService | Create Parameterized Dataset for MicrosoftAccessLinkedService
MongoDbAtlasLinkedService |  | Create Parameterized Linked Service for MongoDbAtlasLinkedService | Create Parameterized Dataset for MongoDbAtlasLinkedService
MongoDbLinkedService |  | Create Parameterized Linked Service for MongoDbLinkedService | Create Parameterized Dataset for MongoDbLinkedService
MongoDbV2LinkedService |  | Create Parameterized Linked Service for MongoDbV2LinkedService | Create Parameterized Dataset for MongoDbV2LinkedService
MySqlLinkedService |  | Create Parameterized Linked Service for MySqlLinkedService | Create Parameterized Dataset for MySqlLinkedService
NetezzaLinkedService |  | Create Parameterized Linked Service for NetezzaLinkedService | Create Parameterized Dataset for NetezzaLinkedService
ODataLinkedService |  | Create Parameterized Linked Service for ODataLinkedService | Create Parameterized Dataset for ODataLinkedService
OdbcLinkedService |  | Create Parameterized Linked Service for OdbcLinkedService | Create Parameterized Dataset for OdbcLinkedService
Office365LinkedService |  | Create Parameterized Linked Service for Office365LinkedService | Create Parameterized Dataset for Office365LinkedService
OracleCloudStorageLinkedService |  | Create Parameterized Linked Service for OracleCloudStorageLinkedService | Create Parameterized Dataset for OracleCloudStorageLinkedService
OracleLinkedService |  | Create Parameterized Linked Service for OracleLinkedService | Create Parameterized Dataset for OracleLinkedService
OracleServiceCloudLinkedService |  | Create Parameterized Linked Service for OracleServiceCloudLinkedService | Create Parameterized Dataset for OracleServiceCloudLinkedService
PaypalLinkedService |  | Create Parameterized Linked Service for PaypalLinkedService | Create Parameterized Dataset for PaypalLinkedService
PhoenixLinkedService |  | Create Parameterized Linked Service for PhoenixLinkedService | Create Parameterized Dataset for PhoenixLinkedService
PostgreSqlLinkedService |  | Create Parameterized Linked Service for PostgreSqlLinkedService | Create Parameterized Dataset for PostgreSqlLinkedService
PrestoLinkedService |  | Create Parameterized Linked Service for PrestoLinkedService | Create Parameterized Dataset for PrestoLinkedService
QuickbaseLinkedService |  | Create Parameterized Linked Service for QuickbaseLinkedService | Create Parameterized Dataset for QuickbaseLinkedService
QuickBooksLinkedService |  | Create Parameterized Linked Service for QuickBooksLinkedService | Create Parameterized Dataset for QuickBooksLinkedService
ResponsysLinkedService |  | Create Parameterized Linked Service for ResponsysLinkedService | Create Parameterized Dataset for ResponsysLinkedService
RestServiceLinkedService |  | Create Parameterized Linked Service for RestServiceLinkedService | Create Parameterized Dataset for RestServiceLinkedService
SalesforceLinkedService |  | Create Parameterized Linked Service for SalesforceLinkedService | Create Parameterized Dataset for SalesforceLinkedService
SalesforceMarketingCloudLinkedService |  | Create Parameterized Linked Service for SalesforceMarketingCloudLinkedService | Create Parameterized Dataset for SalesforceMarketingCloudLinkedService
SalesforceServiceCloudLinkedService |  | Create Parameterized Linked Service for SalesforceServiceCloudLinkedService | Create Parameterized Dataset for SalesforceServiceCloudLinkedService
SapBWLinkedService |  | Create Parameterized Linked Service for SapBWLinkedService | Create Parameterized Dataset for SapBWLinkedService
SapCloudForCustomerLinkedService |  | Create Parameterized Linked Service for SapCloudForCustomerLinkedService | Create Parameterized Dataset for SapCloudForCustomerLinkedService
SapEccLinkedService |  | Create Parameterized Linked Service for SapEccLinkedService | Create Parameterized Dataset for SapEccLinkedService
SapHanaLinkedService |  | Create Parameterized Linked Service for SapHanaLinkedService | Create Parameterized Dataset for SapHanaLinkedService
SapOpenHubLinkedService |  | Create Parameterized Linked Service for SapOpenHubLinkedService | Create Parameterized Dataset for SapOpenHubLinkedService
SapTableLinkedService |  | Create Parameterized Linked Service for SapTableLinkedService | Create Parameterized Dataset for SapTableLinkedService
ServiceNowLinkedService |  | Create Parameterized Linked Service for ServiceNowLinkedService | Create Parameterized Dataset for ServiceNowLinkedService
SftpServerLinkedService |  | Create Parameterized Linked Service for SftpServerLinkedService | Create Parameterized Dataset for SftpServerLinkedService
SharePointOnlineListLinkedService |  | Create Parameterized Linked Service for SharePointOnlineListLinkedService | Create Parameterized Dataset for SharePointOnlineListLinkedService
ShopifyLinkedService |  | Create Parameterized Linked Service for ShopifyLinkedService | Create Parameterized Dataset for ShopifyLinkedService
SmartsheetLinkedService |  | Create Parameterized Linked Service for SmartsheetLinkedService | Create Parameterized Dataset for SmartsheetLinkedService
SnowflakeLinkedService |  | Create Parameterized Linked Service for SnowflakeLinkedService | Create Parameterized Dataset for SnowflakeLinkedService
SparkLinkedService |  | Create Parameterized Linked Service for SparkLinkedService | Create Parameterized Dataset for SparkLinkedService
SqlServerLinkedService |  | Create Parameterized Linked Service for SqlServerLinkedService | Create Parameterized Dataset for SqlServerLinkedService
SquareLinkedService |  | Create Parameterized Linked Service for SquareLinkedService | Create Parameterized Dataset for SquareLinkedService
SybaseLinkedService |  | Create Parameterized Linked Service for SybaseLinkedService | Create Parameterized Dataset for SybaseLinkedService
TeamDeskLinkedService |  | Create Parameterized Linked Service for TeamDeskLinkedService | Create Parameterized Dataset for TeamDeskLinkedService
TeradataLinkedService |  | Create Parameterized Linked Service for TeradataLinkedService | Create Parameterized Dataset for TeradataLinkedService
VerticaLinkedService |  | Create Parameterized Linked Service for VerticaLinkedService | Create Parameterized Dataset for VerticaLinkedService
WebLinkedService |  | Create Parameterized Linked Service for WebLinkedService | Create Parameterized Dataset for WebLinkedService
XeroLinkedService |  | Create Parameterized Linked Service for XeroLinkedService | Create Parameterized Dataset for XeroLinkedService
ZendeskLinkedService |  | Create Parameterized Linked Service for ZendeskLinkedService | Create Parameterized Dataset for ZendeskLinkedService
ZohoLinkedService |  | Create Parameterized Linked Service for ZohoLinkedService | Create Parameterized Dataset for ZohoLinkedService

## Sheet7
AmazonMWSLinkedService
AmazonRdsForOracleLinkedService
AmazonRdsForSqlServerLinkedService
AmazonRedshiftLinkedService
AmazonS3CompatibleLinkedService
AmazonS3LinkedService
AzureBatchLinkedService
AzureBlobFSLinkedService
AzureBlobStorageLinkedService
AzureDatabricksDeltaLakeLinkedService
AzureDatabricksLinkedService
AzureDataExplorerLinkedService
AzureDataLakeAnalyticsLinkedService
AzureDataLakeStoreLinkedService
AzureFileStorageLinkedService
AzureFunctionLinkedService
AzureKeyVaultLinkedService
AzureMariaDBLinkedService
AzureMLLinkedService
AzureMLServiceLinkedService
AzureMySqlLinkedService
AzurePostgreSqlLinkedService
AzureSearchLinkedService
AzureSqlDatabaseLinkedService
AzureSqlDWLinkedService
AzureSqlMILinkedService
AzureStorageLinkedService
AzureTableStorageLinkedService
CassandraLinkedService
CommonDataServiceForAppsLinkedService
ConcurLinkedService
CosmosDbLinkedService
CosmosDbMongoDbApiLinkedService
CouchbaseLinkedService
CustomDataSourceLinkedService
Db2LinkedService
DrillLinkedService
DynamicsAXLinkedService
DynamicsCrmLinkedService
DynamicsLinkedService
EloquaLinkedService
FileServerLinkedService
FtpServerLinkedService
GoogleAdWordsLinkedService
GoogleBigQueryLinkedService
GoogleCloudStorageLinkedService
GreenplumLinkedService
HBaseLinkedService
HdfsLinkedService
HDInsightLinkedService
HDInsightOnDemandLinkedService
HiveLinkedService
HttpLinkedService
HubspotLinkedService
ImpalaLinkedService
InformixLinkedService
JiraLinkedService
MagentoLinkedService
MariaDBLinkedService
MarketoLinkedService
MicrosoftAccessLinkedService
MongoDbAtlasLinkedService
MongoDbLinkedService
MongoDbV2LinkedService
MySqlLinkedService
NetezzaLinkedService
ODataLinkedService
OdbcLinkedService
Office365LinkedService
OracleCloudStorageLinkedService
OracleLinkedService
OracleServiceCloudLinkedService
PaypalLinkedService
PhoenixLinkedService
PostgreSqlLinkedService
PrestoLinkedService
QuickbaseLinkedService
QuickBooksLinkedService
ResponsysLinkedService
RestServiceLinkedService
SalesforceLinkedService
SalesforceMarketingCloudLinkedService
SalesforceServiceCloudLinkedService
SapBWLinkedService
SapCloudForCustomerLinkedService
SapEccLinkedService
SapHanaLinkedService
SapOpenHubLinkedService
SapTableLinkedService
ServiceNowLinkedService
SftpServerLinkedService
SharePointOnlineListLinkedService
ShopifyLinkedService
SmartsheetLinkedService
SnowflakeLinkedService
SparkLinkedService
SqlServerLinkedService
SquareLinkedService
SybaseLinkedService
TeamDeskLinkedService
TeradataLinkedService
VerticaLinkedService
WebLinkedService
XeroLinkedService
ZendeskLinkedService
ZohoLinkedService

## Sheet8
|  |  | 16th | 17th
LOAD | 24hr | hr | 13:30 | 13:30
LOAD | 1hr | hr
LOAD | 4hr | hr
BATCH | 1
6
12